## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Antique Item Gallery |  | 32 | 2021-06-22 | 2021-07-24
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-22 | 2021-08-23 | 2 Days
1.2 | Finish webpage | 2021-08-23 | 2021-08-28 | 6 Days
1.3 | Project Design | 2021-08-29 | 2021-09-02 | 5 Days
2 | Coding
2.1 | Phase 1 | 2021-09-03 | 2021-09-11 | 9 Days
2.2 | Phase 2 | 2021-09-12 | 2021-09-18 | 7 Days
2.3 | Additional Features
3 | Testing
3.1 | Phase 1 Testing | 2021-09-19 | 2021-09-19 | 1 Day
3.2 | Modification /Any changes | 2021-09-19 | 2021-09-19 | 1 Day
3.3 | Phase 2 Testing | 2021-09-20 | 2021-09-20 | 1 Day
3.4 | Modification /Any changes | 2021-09-20 | 2021-09-21 | 2 Days
3.5 | Final Testing | 2021-09-22 | 2021-09-22 | 1 Day
4 | Documentation
4.1 | User Guide | 2021-09-24 | 2021-09-24 | 1 Day
4.2 | Presentation | 2021-09-24 | 2021-09-24 | 1 Day

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Saurabh Gosavi
| PRN No | 210543181028
| Description | Contributing to overall project objective.
2 | Role | Team Member
| Member Name | Shubham Shete
| PRN No | 210543181105
| Description | Contributing to overall project objective.
3 | Role | Team Member
| Member Name | Paresh Bhoi
| PRN No | 210543181059
| Description | Contributing to overall project objective.
4 | Role | Team Member
| Member Name | Sumit Dhanegaonkar
| PRN No | 210543181022
| Description | Contributing to overall project objective.